## Introduction
Cross Code European Network Codes Implementation Plan
Background
On 3 March 2011, the European Third Energy Package came into effect with the aim of developing a more harmonised European energy market. This legislation required the development of European Network Codes (ENCs), which would apply across Europe and take precedence over existing national arrangements. The introduction of the ENCs will have a far reaching impact on the GB electricity industry, with changes required to grid connections, markets and system operation.
Objective
Whilst the final ENCs entered into force in 2017, implementation activities in GB will continue for a number of years. In order for Code Administrators to be able to project manage the required changes these network codes and guidelines will introduce, this document provides the following end to end project plan.
What does the project plan do?
The project plan is designed as a tool with a filter function, to enable the user to select information and tailor it any given audience. Information can be filtered by any variation of the following categories; Code, change reference, ENC, milestones, the date the change was raised, change decision date, implementation date, state of progression (i.e. upcoming, raised, assessment, awaiting implementation etc.), and known dependencies.
Principles
Please be aware that project plan and assessment has been developed on the principle of minimal change to meet compliance, for example to avoid rewriting the newly introduced ENC requirements into the GB Codes.
Please see the summary for the network codes and impacts on the GB Codes below:
| EU Codes and Guidelines | Abbreviations | Description | Status
Connection Codes
| Requirements for Generators | RfG | Harmonise and update technical connection requirements for all types of generators from 800W upward. | Adopted
| Demand Connection Code | DCC | Connection of industrial loads and DSOs, and sets out requirements which will apply to the demand side of the power system. | Adopted
| Network Code on High-Voltage Direct Current Connections | HVDC | Rules for the use of HVDC technology included between synchronous area and embedded systems. | Adopted
Market Codes
| Forward Capacity Allocation | FCA | Couples existing European electricity forward markets to create a pan-European internal market by harmonising market rules for calculating and allocating capacity in the forward market. | Adopted
| Capacity Allocation and Congestion Management | CACM | Rules for allocating capacity in day-ahead and intra-day timeframe, calculating the levels of availability cross border, allocating and recovering costs. | Adopted
| Network Code on Electricity Balancing | EB GL | Rules for cross border exchange of reserves and balancing energy | Adopted
System Operator Codes
| Transmission System Operation Guideline | SOGL | Setting minimum system security, operational planning and frequency management standards. | Adopted
| Network Code on Emergency and Restoration | NC ER | Harmonisation of system defence and restoration procedures during severe events. | Adopted
Need more information?
For more information regarding a specific change, please contact the responsible Code Administrator:
ELEXON |  | Balancing and Settlement Code (BSC)
Energy Networks Association |  | Distribution Code (DCode)
National Grid |  | Connection and Use of System Code (CUSC)
Grid Code (GC)
System Operator – Transmission Owner Code (STC)
What is the publication schedule?
Last Wednesday of every month |  | ELEXON circulate the spreadsheet from the previous month, for NGET and ENA to redline to highlight any updates
First Wednesday of every month |  | NGET and ENA redlines the spreadsheet to highlight any updates, and return the redlined spreadsheet to ELEXON
Second Wednesday of every month |  | ELEXON publishes the updated ENC Implementation Plan on the 'EU Legislation' page of the ELEXON website, and circulate the link to NGET and ENA.
Document management
Version History: ENC Implementation Plan - Mar 18 V1.0 FINAL
This plan offers a best view as the March 2018 updates, as of 10 April 2018.

## Project Plan
Project Plan
The project plan is designed as a tool with a filter function, to enable the user to select information and tailor it towards a given audience. This plan includes all live and upcoming changes. Please note that udpates for March 2018, are highlighted in red.
Code | Change Ref | Title | Timeline Ref | Raise Date Status | Raise Date | Imp Date Status | Imp Date | Implementation Duration | Progression State | Commentary | ENC
|  |  | TODAY | Confirmed | 2018-04-10 | Estimated | 2018-04-11 | 1
Milestone | CACM came into force | CACM came into force | Milestone - CACM came into force | Confirmed | 2015-08-01 | - | - |  | Confirmed | - | CACM
BSC | P344 | Project TERRE implementation into GB market arrangements | BSC - P344 | Confirmed | 2016-06-01 | Estimated | 2019-12-18 | 1295 | Assessment | P344 was raised by National Grid on 1 June 2016. The Modification seeks to align the BSC with the European Balancing Project Trans European Replacement Reserves Exchange (TERRE) requirements. This is in order to allow the implementation of the project at national level and be compliant with the first tranche of obligations in the European Electricity Balancing Guideline EB GL. BSC Panel will make its initial recommendations on the Assessment Report at the May BSC panel as discussed in the work group meeting held on 22 March 2018. | EB GL- Article 19
GC | GC0097 | European Energy Balancing Guidelines - Replacement Reserves - TERRE | GC - GC0097 | Confirmed | 2016-11-16 | Estimated | 2019-12-18 | 1127 | Assessment | GC097 raised by National Grid on 16 November 2016 to address changes associated with project TERRE. Deadline for EIF is fixed. Implementation date has been changed to align with the P344 implementation date. Legal text for this MOD has now been finalised. This Mod will be recommended to the April Grid code Panel. | EB GL - Article 19
BSC | P354 | Use of ABSVD for non-BM Balancing Services at the metered (MPAN) level | BSC - P354 | Confirmed | 2017-01-11 | Estimated | 2019-04-01 | 810 | Assessment | P354 seeks to allow the Transmission Company to provide Applicable Balancing Services Volume Data (ABSVD) for non-BM Balancing Services to BSC Central Systems for allocation to the appropriate Supplier BM Units to correct Suppliers’ Energy Imbalance positions. On 9 January 2018 the P354 workgroup formally discussed and agreed that the Modification discharged the EB GL Article 49 obligations. The P354 Draft Modification Report was presented to the Panel at its meeting on 8 March 2018. The Panel unanimously agreed that the P354 Proposed Modification would better facilitate Applicable BSC Objectives (a), (b), (c), (d) and (e) compared to the current baseline and the P354 Alternative Modification, and should therefore be approved. The P354 Final Modification Report was submitted to the Authority for decision on 9 March 2018. Please note that The recommended Implementation Date for both the P354 Proposed Modification and Alternative Modification is 1 April 2019 as a Standalone Release if an Authority decision is received on or before 30 March 2018; or 1 April 2020 as a Standalone BSC Systems Release if an Authority decision is received after 30 March 2018. | EB GL - Article 49
GC | GC0098 | Using GB Grid Code data to construct the EU Common Grid Model in accordance with Regulation (EU) 2015/1222 (CACM) and Regulation (EU) 2016/1719 (FCA). | GC - GC0098 | Confirmed | 2017-05-30 | Estimated | 2018-08-10 | 437 | Raised | GC0098 was raised by National Grid on 30 May 2017 in response to customers request for greater transparency on data items utilised to great the EU Common Grid Model. The modification was raised as self-governance and the Panel voted for its implementation in September 2017. The Panel decision was appealed to Ofgem in October 2017 which was subsequently upheld by Ofgem in November 2017. The Ofgem decision letter referred back the proposal for further re-consideration and a further Panel self-governance vote. The Modification (including the amended Legal Text) will be submitted to the Panel in April 2018. | CACM/FCA
GC | GC0099 | Establishing a common approach to interconnector scheduling consistent with the single intraday market coupling processes set out within Regulation (EU) 2015/1222 (CACM) | GC - GC0099 | Confirmed | 2017-05-30 | Estimated | 2018-06-01 | 367 | Assessment | GC099 was raised by National Grid on 30 May 2017. Modification has been through workgroup and Code Admin consultation. This modification aligns with P356 | CACM
GC | GC0100 | GC0100 EU Connection Codes GB Implementation – Mod 1 | GC - GC0100 | Confirmed | 2017-05-30 | Estimated | 2018-05-17 | 352 | Raised | This modification will set out within the Grid and Dist Code and the new Engineering Recommendations G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Scope and applicability of the RfG, DCC and HVDC requirements for GB users. 2. Set the x4 Type (A-D) MW banding levels for GB, as required in RfG. 3. Set the GB Fast Fault Current Injection parameters, as set out in RfG. 4. Set the GB Fault Ride Through requirements, as set out in RfG and HVDC NCs. Details of the consultation can be found here - http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0100. This modification was submitted to Ofgem for decision on 20 February 2018. Please note that RFG entered into force 17/05/2016 and needs to be implemented by 2 years after EIF. | RfG/HVDC
Dcode | DC0100 | DC0100 EU Connection Codes GB Implementation – Mod 1 | DCode - DC0100 | Confirmed | 2017-05-30 | Estimated | 2018-05-17 | 352 | Raised | This modification will set out within the Grid and Dist Code and the new Engineering Recommendations G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Scope and applicability of the RfG, DCC and HVDC requirements for GB users. 2. Set the x4 Type (A-D) MW banding levels for GB, as required in RfG. 3. Set the GB Fast Fault Current Injection parameters, as set out in RfG. 4. Set the GB Fault Ride Through requirements, as set out in RfG and HVDC NCs. A DCRP Public consultation closed on the 1 February 2018. Report to Authority submitted 20 February. | RfG/HVDC
GC | GC0101 | GC0101 EU Connection Codes GB Implementation – Mod 2 | GC - GC0101 | Confirmed | 2017-05-30 | Estimated | 2018-05-17 | 352 | Raised | This modification (2/4) will set out within the Grid Dist Code and the new Engineering Recommendatiions G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Set the Voltage & Reactive requirement in GB, as required in RfG and HVDC. 2. Set the Frequency requirements in GB, as required in RfG and HVDC Details of the consultation can be found here - http://www2.nationalgrid.com/UK/Industry-information/Electricity-codes/Grid-code/Modifications/GC0101. This modification was submitted to Ofgem for decision on 20 February 2018. Please note that RFG entered into force 17/05/2016 and needs to be implemented by 2 years after EIF. | RfG/HVDC
Dcode | DC0101 | DC0101 EU Connection Codes GB Implementation – Mod 2 | DCode - DC0101 | Confirmed | 2017-05-30 | Estimated | 2018-05-17 | 352 | Raised | This modification (2/4) will set out within the Grid Dist Code and the new Engineering Recommendatiions G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Set the Voltage & Reactive requirement in GB, as required in RfG and HVDC; and 2. Set the Frequency requirements in GB, as required in RfG and HVDC. A DCRP Public consultation closed on the 1 February 2018. The consultation was seeking comments on the proposed changes needed to implement the required changes as set out above by the RFG. These changes are included in a revised DCode and the introduction of two new Engineering Rcommendations G98 and G99. Report to Authority submitted 20 February. Decision expected 27 March 2018. | RfG/HVDC
BSC | P356 | Time of Interconnector Data Submission | BSC - P356 | Confirmed | 2017-07-01 | Estimated | 2018-11-01 | 488 | Assessment | P356 was raised by National Grid on 3 July 2017. The Modification will align the BSC with Grid Code Modification GC0099, which seeks to introduce the interconnector scheduled transfer process to the Grid Code. This is in order to establish common, cross-code provisions which are compatible with both the EU single intraday market coupling processes, and GB and EU balancing processes. Implementation timeline delayed due to time required to develop WACMs. Now due to be implemented by November 2018 as approved by the BSC panel. The Assessment Report was presented to the BSC Panel on 8 February 2018, the Modification was then issued for Report Phase Consultation. This propsal was approved at the March BSC Panel and is now with the Authority for approval. | CACM
GC | GC0102 | GC0102 EU Connection Codes GB Implementation – Mod 3 | GC - GC0102 | Confirmed | 2017-06-30 | Estimated | 2018-05-17 | 321 | Raised | This modification (3/4) will set out within the Grid and Dist Code and G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Set the System Management parameters, as set out in RfG and HVDC. 2. Set the Compliance requirements, as set out in RfG, and HVDC. This modification was submitted to Ofgem for decision on 20 February 2018. Please note that RFG entered into force 17/05/2016 and needs to be implemented by 2 years after EIF. | RFG
Dcode | DC0102 | DC0102 EU Connection Codes GB Implementation – Mod 3 | Dcode - DC0102 | Confirmed | 2017-06-30 | Estimated | 2018-05-17 | 321 | Raised | This modification (3/4) will set out within the Grid and Dist Code and G98 and G99 the following compliance obligations in the EU Connection Codes: 1. Set the System Management parameters, as set out in RfG and HVDC. 2. Set the Compliance requirements, as set out in RfG, DCC and HVDC. A DCRP Public consultation closed on the 1 February 2018. The consultation was seeking comments on the proposed changes needed to implement the required changes as set out above by the RFG. These changes are included in a revised DCode and the introduction of two new Engineering Rcommendations G98 and G99. Report to Authority submitted 20 February. | RFG
GC | GC0103 | The introduction of harmonised Applicable Electrical Standards in GB to ensure compliance with the EU Connection Codes | GC - GC0103 | Confirmed | 2017-07-27 | Estimated | TBD |  | Raised | GC103 was raised by SSE on 27 July 2017. This modification proposal is intended to harmonise technical standards across GB and where applicable would also align these with the ENCs | -
GC | GC0104 | Demand Connection Code technical requirements, compliance and DSR | GC - GC0104 | Confirmed | 2017-08-16 | Estimated | 2018-09-07 | 387 | Raised | GC104 was rasied by National Grid on 16 August 2017. The modification is joint Grid Code/D Code mods to implement EU Connection Codes into GB and covers all the requirements of DCC not covered in GC 100. This mod is set to be implemented in Q3 2018.Please note DCC entered into force 07/09/2016 and needs to be implemented by 2 years after EIF | DCC
Dcode | DC0104 | Demand Connection Code technical requirements, compliance and DSR | DCode - DC0104 | Confirmed | 2017-08-16 | Estimated | 2018-09-07 | 387 | Raised | DC104 was rasied by National Grid on 16 August 2017. The modification is joint Grid Code/D Code mods to implement EU Connection Codes into GB and covers all the requirements of DCC not covered in GC 100. This mod is set to be implemented in Q3 2018. Workgroup consultation expexted late March 2018. Please note DCC entered into force 07/09/2016 and needs to be implemented by 2 years after EIF. | DCC
BSC | P360 | Making the BSC’s imbalance price compliant with the European Balancing Guideline | BSC - P360 (without Art. 55 derogation) | Confirmed | 2017-09-07 | Estimated | 2018-11-01 | 420 | Assessment | P360 was raised by National Grid on 7 September 2017. The modification seeks to implement changes to the BSC, to ensure compliance with EB GL Article 55. A derogation from Article 55 is currently being sought. Should a derogation be granted, this Modification will likely be withdrawn. | EB GL - Article 55
Milestone | Milestone | SOGL came into force | Milestone - SOGL: Entry into force | Confirmed | 2017-09-14 | - | - |  | Confirmed | The Transmission System Operation Guideline (SOGL) entered into force 14 September 2017 | SOGL
GC | GC0106 | European SOGL Implementation - Data Exchange | DCode - GC0106 | Confirmed | 2017-10-12 | Estimated | 2018-10-01 | 354 | Raised | Raised by National Grid on 12 October 2017, and is joint working with Dcode. This Modification seeks to make changes to data exchange requirements in the Grid Code arising from the EU regulation SOGL Data Exchange Methodology (KORRR). | SOGL
Dcode | DC0106 | European SOGL Implementation - Data Exchange | Dcode - DC0106 | Confirmed | 2017-10-12 | Estimated | 2018-10-01 | 354 | Raised | Raised by National Grid on Grid Code and Dist Code 12 October 2017, and is joint working with Grid Code. This Modification seeks to make changes to data exchange requirements in the DCode arising from the EU regulation SOGL Data Exchange Methodology (KORRR). Work ongoing. | SOGL
GC | GC0107 | The open, transparent, non-discriminatory and timely publication of the generic and/or PGM specific values required to be specified by the relevant TSO(s) and / or relevant system operator et al., in accordance with the RfG | GC - GC0107 | Confirmed | 2017-11-15 | Estimated | TBD |  | Raised | GC107 was raised by SSE in November 17 panel, first workgroup is to be arranged. | RfG
Milestone | Milestone | EB GL entry into force | Milestone - EB GL: Entry into force | Confirmed | 2017-12-18 | - | - |  | Confirmed | The Regulation establishing a guideline on electricity balancing (EB) was adopted on 23 November 2017 and will enter into force on 18 December 2017. The EB guideline will set down rules on the operation of balancing markets, i.e. those markets that Transmission System Operators (TSOs) use to procure energy and capacity to keep the system in balance in real time. The guideline's provisions include increasing the opportunities for cross-border trading close to real-time and improve the efficiency of balancing markets in Europe | EB GL
Milestone | Milestone | Assignment of EB GL where needed | Milestone - EB GL: Assignment | Confirmed | 2017-12-18 | - | - |  | Confirmed | BEIS assigned the relevant on the 18/12/17. | EB GL
Milestone | Milestone | NC ER comes into force | Milestone - NC ER: Entry into force | Confirmed | 2017-12-18 | - | - |  | Confirmed | The Regulation establishing a network code on emergency and restoration (ER) was adopted on 24 November 2017 and will enter into force on 18 December 2017. The ER network code will set down rules relating to the management of the electricity transmission system in emergency, blackout and restoration states. Its provisions are mainly related to bringing the system back to a normal state. | NC ER
GC | GC0108 (Previously Grid Code Potential Change 4) | EU Code: Emergency & Restoration: Black start tesing requirement | GC - GC0108 | Confirmed | 2018-02-01 | Estimated | TBD |  | Raised | This mod was raised at the Feb 18 Grid Code panel, an issue identified with proposed techincal solution. Issue was addressed via re submission at March panel which now will proceed to Code Admin consultation. | NC ER
GC | Grid Code Potential Change 12 | European SOGL - Requirements FCR; FRR; FRR prequalification and minimum technical requirements and items related to Interconnector Ramp-Rate restrictions | GC - SOGL: Requirements | Estimated | 2018-04-07 | Estimated | TBD |  | Upcoming | NGET’s current view is that this mod is not required, a request for further clarification on the reasoning behind this position has been raised via GCRP and we are in the process of working with both GCRP and GCDF to clarify the points raised. This modification will remain on the Forward Work Plan until discussions are completed. | SOGL
CUSC | CUSC Potential Change 1 | European Energy Balancing Guidelines - Replacement Reserves | CUSC - EB GL: Replacement Reserves | Estimated | 2018-04-19 | Estimated | 2019-04-30 | 376 | Upcoming | NGET will raise this mod at the April CUSC Panel. | EB GL
Milestone | Milestone | Application for Exemption from 15 min Settlement | Milestone - EB GL: Application for Exemption from 15 min Settlement | Estimated | 2018-06-18 | Confirmed | 2020-03-18 | 639 | Assumed | - | EB GL
Milestone | Milestone | Backstop date for submission of derogation requests from Article 49 and 55 | Milestone - EB GL: Backstop forArt. 49 and 55 derogation requests | Confirmed | 2018-06-18 | - | - |  | Confirmed | - | EB GL - Article 49 & 55
GC | Grid Code Potential Change 11 | European SOGL Implementation - Regional Outage Coordination | GC - SOGL: Regional Outage Coordination | Estimated | 2018-09-07 | Estimated | TBD |  | Upcoming | This mod is set to be raised during Q 3 2018 and is linked to the development of the Regional Outage Coordination methodology, requirements will become clearer as part of methodology development. | SOGL
GC | Grid Code Potential Change 16 | Regional Outage Co-ordination and Security Analysis | GC - SOGL: Regional Outage Co-ordination and Security Analysis | Estimated | 2018-09-07 | Estimated | TBD |  | Upcoming | The methodology is currently being developed and requirements on this modification will become clearer as part of this development.This mod is set to be raised at the end of Q3 2018 | SOGL
STC | STC Potential Change 3 | European SOGL Implementation -Regional Outage Coordination | STC - SOGL: Regional Outage Coordination | Estimated | 2018-09-07 | Estimated | TBD |  | Upcoming | This is linked to the development of the Regional Outage Coordination methodology, requirements will become clearer as part of methodology development. | SOGL
GC | Grid Code Potential Change 15 | European Energy Balancing Guidelines- Manual Frequency Restoration Reserves | GC - EB GL: Manual Frequency Restoration Reserves | Estimated | 2018-12-01 | Estimated | TBD |  | Upcoming | We are unlikely to have sufficient information from the central mFRR project in order to raise this mod before the end of next year. This mod is needed in order to implement the mFRR product into GB Grid code arrangements, and will be based on the approach used to implement RR into the Grid Code (GC 0097) | EB GL - Article 20
BSC | BSC Potential Change 5 | Activation Purposes proposal leading to corresponding changes to Imbalance Price calaculations | BSC - EB GL: Amendments to Imbalance Price | Estimated | 2018-12-18 | Estimated | 2020-06-01 | 531 | Upcoming | If TSO Proposal for activation purpose do not align with the BSC, this Modification will be raised to amend the imbalance price calculation | EB GL - Article 29
Milestone | Milestone | UK leaves EU | Milestone - UK leaves EU | Confirmed | 2019-03-29 | - | - |  | Confirmed | - | -
BSC | BSC Potential Change 11 | Harmonised Imbalance Settlement (with Article 55 derogation) | BSC - EB GL: Harmonised Imbalance Settlement (with Art. 55 derogation) | Estimated | 2019-06-01 | Confirmed | 2020-11-01 | 519 | Upcoming | This Modification will be raised to align the BSC with NGETs proposals to harmonise the main features of imbalance settlement. If a derogation for EB GL Article 55, it is likely that P360 will be withdrawn and the work to date will be included within this Modification. | EB GL - Article 55
BSC | BSC Potential Change 12 | European Energy Balancing Guidelines- Manual Frequency Restoration Reserves | BSC - EB GL: Project MARI | Estimated | 2019-06-01 | Estimated | 2021-12-18 | 931 | Upcoming | This Modification will be raised, as an extension of the principles introduced under P344 'Project TERRE' in order to implement the Manual Frequency Restoration Reserves (mFRR) process into the BSC as required under the EB GL. | EB GL - Article 20
Milestone | Milestone | Backstop date for RR standard products | Milestone - EBGL: Backstop date for RR standard products | Confirmed | 2019-12-18 | - | - |  | Assumed | the RR platform must be made operational by two years after entry into force. Entry into force is now confirmed as 18th Dec 2018. | EB GL
Milestone | Milestone | Earliest decision on bidding zone change | Milestone - Earliest decision on bidding zone change | Estimated | 2020-07-01 | - | - |  | Assumed | - | CACM
CUSC | CUSC Potential Change 2 | European Energy Balancing Guidelines - Manual Frequency Restoration Reserves | CUSC - EB GL: mFRR | Estimated | 2020-07-01 | Estimated | 2021-07-01 | 365 | Upcoming | This mod is set to be raised Q3 2020.This mod is set to be implemented in Q3 2021. Further work is being done to confirm if the mod is required and understand the scope of this however if CUSC Potential mod 1 is raised this modification may be unnecessary. | EB GL - Article 20
Milestone | Milestone | Backstop date for harmonised Imbalance Settlement | Milestone - Backstop date for harmonised Imbalance Settlement | Confirmed | 2020-12-18 | - | - |  | Assumed | - | EB GL
Milestone | Milestone | Implementation date for any bidding zone change | Milestone - Implementation date for any bidding zone change | Estimated | 2021-07-01 | - | - |  | Assumed | - | CACM
Milestone | Milestone | Backstop date for FRR standard products (mFRR and aFRR) | Milestone - Backstop date for FRR standard products | Confirmed | 2021-12-18 | - | - |  | Assumed | GB do not expect to implement the aFRR product. | EB GL
STC | STC Potential Change 2 | European SOGL Implementation - Data Exchange | STC - SOGL: Implementation - Data Exchange | Confirmed | TBD | Estimated | TBD |  | Upcoming | This is linked to the development of the KORRR methodology, requirements will become clearer as part of KORRR development and the detailed code mapping of the SOGL data exchange articles in January 2018. NGET presented at STC Panel in January providing detailed reasoning as to why this modification is not required however it shall remain on the workplan until discussions are fully completed. | SOGL
GC | Grid Code Potential Change 13 | Emergency & Restoration Code - Market Suspension | GC - NC ER: Market Suspensions | Estimated | TBD | Estimated | TBD |  | Upcoming | Deadline for EIF is provisionally Q4 2018, however this mod will only be raised if Black Start limits need to be changed. NGET's current view is that this modification is not needed as current GC rules are consistent with ER. This rationale will be validated through revisiting our code mapping to ensure that all compliance requirements are met. This mod will remain on workplan until discussions are complete. | NC ER
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Closed changes
Closed changes
This list includes changes that have been implemented, withdrawn, in hiatus or are no longer required. Please note that updates for March 2018, are highlighted in red.
Code | Change Ref | Title | Timeline Ref | S | Raised | S | Imp Date | Implementation Duration | Progression State | Commentary | ENC
SQSS | GSR012 | Treatment of Interconnectors | SQSS - GSR012 | C | 2010-10-05 | E | TBD | 1 | Hiatus | Workgroup meetings need to re-convene following 1 year hiatus. This change will appear on the plan when the Workgroup reconvenes.
CUSC | CMP279 | Housekeeping modification to amend typographical errors in the CMP272 legal text | CUSC - CMP279 | E | 2017-04-19 | E | 2017-05-31 | 42 | Implemented | This modification was implemented in the CUSC on the 31 May 2017
Dcode | DCRP1701 | Entry into Force of the EU Network Code “Transmission System Operational Guideline | Dcode - DCRP1701 | E | 2016-12-08 | E | 2017-05-01 | 144 | Implemented | The GB Distribution Code requires two minor modifications to DOC5 and DOC7 to ensure it is compliant with the EU Network Code “Transmission System Operation Guidelines” (TSOG). The TSOG is expected to enter into force in early summer 2017 and some parts of it are effective immediately. On the 28/04/2017 the Authority published its decision and approve the modification. The modification was implemented on 01/05/2017. | SOGL
BSC | P329 | REMIT | BSC - REMIT | C | 2015-11-25 | C | 2017-06-29 | 582 | Implemented | P329 aligned the BSC and BMRS with the Regulation on Wholesale Energy Markets Integrity and Transparency (REMIT) common schemas for inside information web feeds, required by the Agency for the Cooperation of Energy Regulators (ACER). To achieve this, the REMIT inside information data submitted by participants and reported by the BMRS will need to cover the output requirements of ACER. In addition to the ACER requirements, P329 enables the submission of outage profile information to BMRS. BSC Parties will be ultimately responsible for both accuracy and timeliness of their REMIT messages. | REMIT
STC | STC Potential Change 1 | European TSOG - Multi TSO Training Cooperation | STC - STC Potential Change 1 | E | 2017-10-01 | C | 2018-10-01 | 0 | Not required | The SOGL article 63 is an SO only article focusing on operational tasks performed by SOs. No additional training obligation between the SO and TO roles is deemed necessary as part of SOGL implementation and hence no change to the STC is required | SOGL
GC | Grid Code Potential Change 17 | SOGL Requirements in Relation to Reserve Providers and Operational Agreements | GC - Grid Code Potential Change 17 | E | 2017-12-01 | E | TBD | 0 | Not required |  | SOGL
BSC | BSC Potential Change 7 | Project TERRE 2 | BSC - BSC Potential Change 7 | E | 2018-10-01 | E | 2020-03-01 | 0 | Not required | This Modification will be raised to implement any outstanding activities from Project TERRE | EB GL
BSC | BSC Potential Change 9 | NGET proposal on specific products | BSC - BSC Potential Change 9 | E | 2018-11-01 | E | 2019-11-07 | 0 | Not required | If NGET make a proposal on specific products, an assessment will be required to ensure that the understanding of specific products aligns with the BSC. If understanding of specific products in the TSO proposal, differs from the BSC, this Modification will be raised to align the BSC with the proposal. | EB GL
BSC | BSC Potential Change 10 | Market Suspension and Restoration Arrangement | BSC - BSC Potential Change 10 | E | 2018-11-01 | E | 2020-03-01 | 0 | Not required | If NGET makes proposals for rules concerning the suspension and restoration of market activities; and the rules for balancing energy and imbalance settlement during market suspension, that differ from the BSC, this Modification will be raised to align the BSC with the proposals. | NC ER
BSC | BSC Potential Change 8 | Unintended exchanges of energy | BSC - BSC Potential Change 8 | E | 2018-12-01 | E | 2019-11-07 | 0 | Not required | Certainty on whether this Mod is required, is based on the provision of information from NGET, on what will be proposed. | EB GL
BSC | BSC Potential Change 13 | Project TERRE 3 | BSC - BSC Potential Change 13 | E | 2019-01-01 | E | 2020-02-27 | 0 | Not required | This Modification will be raised to implementation outstanding activities from P344 'Project TERRE' | EB GL
GC | GC0095 | GB implementation workgroup for Transmission System Operation Guideline (TSOG) European Network Code | GC - GC0095 | C | 2016-05-27 | E | TBD | 0 | Withdrawn | This modification was set up as an issue group. This was historcially given a Modification reference prior to Open Governance and actually served as an issues group. The change has now been withdrawn, and the new Modification which has arisen from the TSOG guidelines is GC0106 SOGL. | SOGL
BSC | P342 | Change to Gate Closure for Energy Contract Volume Notifications | BSC - P342 | Confirmed | 2016-05-25 | Confirmed | 2017-11-02 | 526 | Implemented | This Modification would introduce a new deadline for the purpose of submitting Energy Contract Volume Notifications (ECVNs) and Metered Volume Reallocation Notifications (MVRNs) for each Settlement Period. This new contract notification deadline would be decoupled from Gate Closure, and would be at the start of the relevant Settlement Period (Alternative Modification). | -
GC | GC0091 | Application of the the Demand Connection Code - Implementation of European Network Code | GC - GC0091 | Confirmed | 2016-03-01 | Estimated | TBD | 1 | Withdrawn | This modification was originally set up as an issue Group. This has been requested to be withdrawn at the August Grid Code panel and September Distribution Code Panel. | DCC
GC | Grid Code Potential Change 10 | Frequency Restoration Reserves | GC - EB GL: FRR | Estimated | 2020-01-01 | Estimated | 2021-07-01 | 547 | Not required | This mod is set to be raised in Q1 2020. Deadline for EIF is provisionally Q3 2021. This is a repitition of row 40 below (No mod for aFRR is expected as we do not expect to implement theproduct). | EB GL
GC | Grid Code Potential Change 2 | European Energy Balancing Guidelines - General Compliance | GC - EB GL: General Compliance | Estimated | 2020-01-01 | Estimated | 2021-07-01 | 547 | Not required | This modification maybe required to address general compliance requirements of the EB GL. The mod if currently set to be raised in Q1 2020. Deadline for EIF is fixed. The mod is set to be implemented in Q3 2021. | EB GL
BSC | BSC Potential Change 4 | Align BSC with the Authority's oversight obligation | BSC - EB GL: Align BSC with the Authority's oversight obligation | Estimated | 2018-03-18 | Estimated | 2018-12-18 | 275 | Not required | Assignment by BEIS and decision by Ofgem on how it wishes to approach this requirement | EB GL
BSC | BSC Potential Change 6 | Align BSC with the TSO's Terms and Conditions | BSC - EB GL: Align BSC with the TSO's T&Cs | Estimated | 2018-12-01 | Estimated | 2019-11-07 | 341 | Not required | If NGET write Ts & Cs in a way that differs from the Ts & Cs of the BSC, this Modification will be raised to align the BSC with the Ts & Cs of the TSO. | EB GL
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (without Article 49 derogation) | BSC - EB GL: Inclusion of Imbalance Adjustments (without Art. 49 derogation) | Estimated | 2018-01-11 | Estimated | 2018-11-01 | 294 | Upcoming | It is assumed that NGET and ELEXON will apply for a derogation for Article 49. If a derogation is not granted, this Modification will be raised in June 2019. | EB GL
BSC | BSC Potential Change 3 | Inclusion of Imbalance Adjustments (with Article 49 derogation) | BSC - EB GL: Inclusion of Imbalance Adjustments (with Art. 49 derogation) | Estimated | 2019-06-01 | Estimated | 2020-11-01 | 519 | Upcoming | It is assumed that NGET will apply for a derogation for EB GL Article 49. If a derogation is granted, this Modification will be raised in June 2019 | EB GL